## Sheet1
Project Information | BID PKG # | CONTRACTOR | CONTRACTOR LIC. # | O&M | Warranty | KEYS | TRAINING | AS-BUILTS | PUNCHLIST COMPLETE | Retention Paid w/ Conditional Release | Uncond. Release RCVD. | FEC Prep'd for Sending (*indicates incomplete FEC) | FEC SENT | Notice of Completion / FINAL DRAFT for Signature | Notice of Completion / Final to Board | RETENTION PAID | UNCOND. RELEASE RECEIVED | Notice of Completion / DRAFT | Notice of Completion/Final to Board | Notice of Completion - Recorded Document # & Date | RECORDING FEE | DSA 6C - Final Verified Report / DRAFT | DSA 6C TO Contractor | RESENT | RETURNED | DSA 6C FINAL LOADED TO DSA BOX | DSA 152 CARD NO. | DSA 6AE Final Verified Report NEEDED | DSA 6PI | DSA 102-IC | DSA 102 NEEDED | DSA 108 | Misc. Lab Reports | Geotech Reports | DSA 301N | DSA 301P | DSA 168 Final Project Cost Needed | Re-Exam Fee Due $ | Final Fee Recon by DSA | Notice to Proceed | Signed Agmt to Contractor | FEC to Contractor